SECTION 108

PROSECUTION AND PROGRESS OF WORK

I. PATENT FEES AND ROYALTIES

1.1 The Contractor shall pay all license fees and royalties and assume all costs incident to the use in the performance of the Work or the incorporation in the Work of any invention, design, process, product or device which is the subject of patent rights or copyrights held by others. If a particular invention, design, process, product or device is specified in the Contract Documents for use in the performance of the Work and if to the actual knowledge of the Owner its use is subject to patent rights or copyrights calling for the payment of any license fee or royalty to others, the existence of such rights shall be disclosed by the Owner in the Contract Documents.

1.2 To the fullest extent permitted by Laws and Regulations, the Contractor shall indemnify and hold harmless the Owner, the Engineer, the Engineer’s Consultants and the officers, directors, employees, agents and other consultants of each and any of them from and against all claims, costs, losses and damages arising out of or resulting from any infringement of patent rights or copyrights incident to the use in the performance of the Work or resulting from the incorporation in the Work of any invention, design, process, product or device not specified in the Contract Documents.

II. TAXES

2.1 The Contractor shall pay all sales, consumer, use and other similar taxes required to be paid by the Contractor in accordance with the Laws and Regulations of the Project that are applicable during the performance of the Work. (The Contractor may apply to the Virginia Department of Environmental Quality for tax exempt status for certain wastewater products.)

III. NOTICE TO PROCEED

3.1 Written Notice to Proceed will be given after the Agreement has been executed and the required Bid Security and insurances have been filed with and approved by the Owner.

3.2 The Contractor shall notify the Owner and all other governing bodies having jurisdiction, of the time and location that Work will begin at least 48 hours prior to beginning Work.

IV. PRE-CONSTRUCTION CONFERENCE

4.1 Within ten (10) Days of the Effective Date of the Agreement, a conference attended by the Contractor, the Owner, and others as appropriate will be held to discuss the Project, and to discuss procedures relating to Shop Drawings, submittals, Applications for Payment, and other Project issues, and to establish a working relationship among the parties as to the Work.
V. CONSTRUCTION PROGRESS SCHEDULE

5.1 Within ten (10) Days after the Effective Date of the Agreement, the Contractor shall submit a written schedule to the Owner showing the proposed order of Work and indicating the time required for completion of major items of Work. This schedule shall take into account the passage or handling of traffic with the least practicable interference and the orderly, timely and efficient prosecution of the Work. The schedule will be used as an indication of the sequence of the major construction operations and as a check on the progress of the Work.

A. A construction schedule in the form of a critical path shall be submitted to the Owner as part of the submittal process prior to beginning construction and shall be updated when duration or sequencing changes.

B. Upon receipt of an approved “Work Schedule”, the Contractor shall submit to the Owner, within 10 days,

1. An estimated payment schedule by each month of project duration.

2. A composite curve to show the estimated value of Work completed and stored materials less specified retainage.

3. Key months when work will be 50, 80, 90, and 100 percent complete shall be established.

4. Identification when facilities will be fully operational.

C. During the course of Work, the Contractor shall update with new composite curves at key months or whenever variation is expected to be more than plus or minus 10 percent.  The original or previous composite curves shall be retained as dashed curves on all updates.

D. The Owner reserves the right to audit all reports and schedules.  For cost-reimbursement contracts, change orders issued for fixed priced contracts or other contracts in excess of $30,000, which include the provisions of services, the Contractor shall retain all books, records and other documents relative to this contract for five (5) years after final payment or until audited by the Owner or designee, whichever is sooner.  The Owner and its authorized agents shall have full access to and the right to examine and duplicate any of said materials during said period.

5.2 The Contractor shall update the progress schedule monthly to reflect any schedule changes required to complete the remaining Work in accordance with the requirements of the Contract Documents. The updated schedule shall be submitted to the Owner for acceptance with the monthly application for progress payment; no payment will be made if the updated schedule is not submitted. All proposed adjustments in the progress schedule shall generally conform to the progress schedule then in effect and will comply with any provisions of the general requirements applicable thereto.

VI. SUBCONTRACTS

6.1 Except as otherwise noted, contract Work, the cost of which is at least fifty percent (50%) of the total Contract Price shall be performed by the Contractor’s own organization.
6.2 No part of the Work shall be transferred or subcontracted without prior written consent of the Owner, and no such consent or approval shall release the Contractor from any obligations to the Owner or persons employed by the Subcontractors, or to those supplying materials to the Subcontractors.

6.3 The Contractor agrees that it is as fully responsible to the Owner for the acts and omissions of its Subcontractors and persons either directly or indirectly employed by the Subcontractors as it is for the acts or omissions of persons directly employed.

6.4 Nothing contained in the Agreement shall create any contractual relation between any Subcontractor and the Owner. 
VII. COMMENCEMENT AND PROSECUTION OF WORK

7.1 The Contractor shall commence Work within ten (10) Days of the date specified in the Notice to Proceed. Time being of the essence of this Project, the Contractor shall prosecute the Work diligently, using such means and methods of construction as will secure its full completion within the time period specified in the Agreement. No Work shall be done at the site prior to the date specified in the Notice to Proceed.

7.2 The Contractor shall proceed with the Work at such rate of progress to insure full completion within the Contract Time. It is expressly understood and agreed, by and between the Contractor and the Owner, that the Contract Time for the completion of the Work as specified in the Agreement is a reasonable time, taking into consideration the average climatic and economic conditions and other factors prevailing in the locality of the Project.

7.3 The Contract Time will commence on the date indicated in the Notice to Proceed. 

7.4 Once the Contractor has commenced Work, it shall be prosecuted continuously and to the fullest extent possible except for interruptions caused by delays authorized or ordered by the Owner by a Change Order or by weather.

Contractor agrees that it will make no claim for increased Contract Price or extended Contract Time arising from delay except by request for a Change Order as set forth below.  The Contract Time may be extended and/or Contract Price may be increased by Change Order if the Owner determines that:

A. the Contractor is delayed in the progress of Work by any act or omission of the Owner or the Engineer, or by any separate contractor employed by the Owner, or by strikes, lockouts, fire, adverse weather conditions not reasonably anticipated, or acts of nature;
B. such delay affects the overall completion of the Work;

C. the Contractor gives written Notice to the Owner within 48 hours of the start of the occurrence, stating the cause of the potential delay and estimate of the possible Contract Time extension involved; and

D. the Contractor gives written Notice to the Owner of any actual Contract Time extension and/or Contract Price increase requested as a result of the aforementioned occurrences within 10 days after the delay has been remedied.

7.5 Gifts, gratuities, or favors shall not be given or offered by the Contractor to personnel of the Owner.

7.6 The Contractor shall not employ any personnel of the Owner or the Engineer for any services without the prior written consent of the Owner.

7.7 Workers shall have sufficient skill and experience to perform properly the Work assigned to them. Workers engaged in special or skilled Work shall have sufficient experience in such Work and in the operation of equipment required to perform it properly and satisfactorily. Any person employed by the Contractor or any Subcontractor who, in the opinion of the Owner, does not perform his Work in a proper and skillful manner or is intemperate or disorderly shall, at the written request of the Owner, be removed forthwith by the Contractor or Subcontractor employing the person and shall not be employed again on any portion of the Work without the approval of the Owner.

7.8 Equipment shall be of sufficient size and in such mechanical condition as to meet the requirements of the Work and produce a satisfactory quality of Work. Equipment and the Contractor’s methods and means shall be such that no damage to the roadway, adjacent property, or other highways will result from its use. The Owner may order the removal and require replacement of unsatisfactory equipment.

VIII. SUSPENSION OF WORK

8.1 The Owner may, at any time and without cause, suspend the Work or any portion thereof for a period of not more than 90 Days or such further time as agreed upon by the Contractor, by Written Notice to the Contractor. Such Notice shall specify the date on which Work shall be resumed and the Contractor shall resume the Work on the date so specified. The Contractor will be allowed an increase in the Contract Price or an extension of the Contract Time, or both, directly attributable to any suspension if the Contractor makes a claim in accordance with the Contract Documents, except that no such increase or extension shall be allowed if the suspension was due to a failure by the Contractor to perform the Work in accordance with the Agreement.

8.2 The Owner may decline to approve or, because of subsequently discovered evidence, nullify the whole or part of any Application for Payment to such extent as may be necessary to protect the Owner from loss on account of:

A. Defective Work not remedied;
B. Claims filed or reasonable evidence indicating probable filing of claims against the Contractor;
C. Failure of the Contractor to make payments properly to subcontractors or for materials or labor;
D. A reasonable doubt that the Contract can be completed for the balance then unpaid;
E. Failure to maintain (each month) the record set of drawings and specifications, or a failure to provide the Owner record drawings and specifications within 30 calendar days from the date of the Certificate of Substantial Completion;
F. Failure to periodically remove and dispose of accumulated debris, rubbish, and discarded/damaged materials;
G. Persistent failure to carry out the Work in accordance with the Contract Documents;
H. A reasonable doubt that the Work will be completed within the Contract Time.

8.3 When the above grounds are resolved to the satisfaction of the Owner, payment shall be made for amounts withheld therefore.
IX. TERMINATION OF AGREEMENT

9.1 Termination for the Convenience of the Owner
The performance of Work under this Agreement may be terminated by the Owner in accordance with this section in whole, or in part(s), whenever the Owner shall determine that such termination is in the best interest of the Owner. Any such termination shall be effected by delivery to the Contractor of a notice of termination specifying the extent to which performance of Work under the Agreement is terminated, and the date upon which such termination becomes effective.

After receipt of a notice of termination, and except as otherwise directed by the Owner, the Contractor shall:

A. Stop Work under the Agreement on the date and to the extent specified in the notice of termination.

B. Place no further orders or subcontracts for mater​ials, services, or facilities, except as may be necessary for completion of such portion of the Work under the Agreement that is not terminated.

C. Terminate all orders and subcontracts to the extent that they relate to the performance of the Work terminated by the notice of termination.

D. Assign to the Owner, and as directed by the Owner, all of the right, title and interest of the Contractor under the orders and subcontracts so terminated. The Owner shall have the right and discretion to settle or pay any and all claims arising out of the termination of such orders and subcontracts.

E. Settle all outstanding liabilities and all claims arising out of such termination of orders and subcontracts, with the approval or ratification of the Owner. This approval or ratification will be final for all purposes of this section.

F. Transfer title and deliver to the Owner, as directed by the Owner, the fabricated or unfabricated parts, Work in process, completed Work, supplies, and other materials produced as a part of or acquired in connection with the performance of the Work terminated by the notice of termination, and the completed or partially completed plans, drawings, information and other property which, if the Agreement has been completed, would have been required to be furnished to the Owner.

G. Use his best efforts to sell as directed or authorized by the Owner, property of the type referred to in Paragraph F above; provided, however, that the Contractor shall not be required to extend credit to any purchaser. The proceeds of any such transfer or disposition shall be applied in reduction of any payments to be made by the Owner to the Contractor under this Agreement or shall otherwise be credited to the Contract price or cost of the Work covered by this Agreement or paid in such manner as directed by the Owner. The Contractor may acquire any such property under the conditions prescribed and at a price or prices approved by the Owner.

H. Complete performance of that Work which was not terminated by the Owner.

I. Take such action as may be necessary, or as the Owner may direct, for the protection and preserva​tion of the property related to this Agreement which is in the possession of the Contractor and in which the Owner has, or may acquire, an interest.

J. Within 30 Days after the receipt of the Notice of termination, the Contractor may submit a list to the Owner for approval, certified as to quantity and quality of any or all items of, inventory not previously disposed of, exclusive of items, the disposition of which has been directed or authorized by the Owner, and may request the Owner to remove such approved items or enter into a storage agreement covering the same. Not later than 15 Days thereafter, the Owner will accept title to such approved items and remove them or enter into a storage agreement covering same. The list submitted shall be subject to final verification by the Owner upon removal of the items, or if the items were stored within 45 Days from the date of submission of the list. Any necessary adjustment to correct the list as submitted shall be made prior to final settlement.

K. Within 30 Days after receipt of the notice of termination, the Contractor shall submit to the Owner his termination claim. Such claim shall be submitted in writing. Upon failure of the Contractor to submit its termination claim within the time allowed, the Owner may, at its discretion, reject such termination claim. Such termination claim shall include the cost of the following:

1. The cost of supplies accepted by the Owner and not previously paid for by the Owner, appropriately adjusted for any saving of freight or other charges.

2. The cost incurred in the performance of the Work terminated, including Initial cost and preparatory expense allocable thereto, but exclusive of any cost attributable to supplies paid or to be paid for by the Owner.

3. The cost of settling and paying claims arising out of the termination of Work under subcontracts or orders which are properly chargeable to the termi​nated portion of the Agreement, exclusive of amounts paid or payable on account of supplies or materials delivered or services furnished by Subcontractors or vendors prior to the effective date of notice of termination and previously paid for by the Owner.

4. A reasonable amount of profit or commission, which will be determined based on the Project's specific overhead and expense data at the rate computed in the original Contract Price or, at the discretion of the Owner, as determined by an audit. The cost of the audit will be borne by the Contractor.

5. Cost of reasonable storage, transportation and other costs incurred in connection with the protection or dispo​sition of property allocable to this termination portion of the Agreement.

6. The total sum to be paid to the Contractor shall not exceed the Contract Price as reduced by the amount of payments previously made and its further reduced by the Contract Price of Work not terminated. Said total sum shall also be reduced by the reasonable value, as determined by the Owner, of property which is destroyed, lost, stolen, or damaged so as to become undeliverable to the Owner or to a buyer.

9.2 Termination with Cause/Default

In the event that the Contractor shall for any reason or through any cause be in default of the terms of this Agreement, the Owner may give the Contractor written Notice of such default by certified mail/return receipt requested at the address set forth herein.

Unless otherwise provided, Contractor shall have ten (10) Days from the date such notice is mailed in which to cure the default. Upon failure of the Contractor to cure the default, the Owner may immediately cancel and terminate this Agreement as of the mailing date of the default notice.

Upon termination, the Contractor shall withdraw its personnel and equipment, cease performance of any further Work under this Agreement, and turn over to the Owner any Work in process for which payment has been made.

In the event of violations of law, safety or health standards and regulations, this Agreement may be immediately canceled and terminated by the Owner and provisions herein with respect to opportunity to cure default shall not be applicable.

9.3 Contractor’s Right to Terminate the Agreement

Should the Work be stopped for a period of 90 Days or more, through no fault of the Contractor, or should the Owner fail to pay the Contractor any payment within a reasonable length of time after said payment shall become due, the Contractor may, upon seven (7) Days written notice to the Owner, stop Work, or terminate the Agreement and recover from the Owner payment for all Work executed, plus any loss actually sustained, plus reasonable profit and damage; provided, however, the total recovery from Owner shall not exceed the Contract Price.

X. LIQUIDATED DAMAGES

10.1 It is mutually understood and agreed by and between the Contractor and Owner that in the execution of the Work, time is an essential element of the Agreement, and it is important that the Work proceed vigorously to completion.

10.2 The Owner has the right to deduct any liquidated damages from any money in the Owner’s hands, otherwise due, or to become due, to the Contractor, and to sue for and recover any additional compensation for damages for non-performance of the Work or failure to complete the Work within the Contract Time. 
10.3 The assessment of liquidated damages for failure to complete the Work within the Contract Time shall not constitute a waiver of the Owner’s right to collect any additional damages that the Owner may sustain by failure of the Contractor to carry out the terms of the Agreement. 
10.4 In the event of delay in the completion of the Work as specified beyond the Completion Date as adjusted by Change Orders, it would be difficult to determine the exact amount of the loss or damages suffered by the Owner due to delays in completion of the Agreement. Therefore, for every -Day of delay past Completion Date of this Agreement as adjusted by Change Orders, the Contractor and the Contractor’s Surety will be liable to the Owner, as liquidated damages for delay and not as a penalty, in the sum designated in Section 102, III. Bid Form, and in paragraph H of the Agreement between Contractor and Owner as set forth in Section 103, for each and every calendar Day the Contractor shall be in default, as follows:  

A. If Substantial Completion has not been achieved by the scheduled Substantial Completion date, the Substantial Completion liquidated damages shall accrue each Day until Substantial Completion is achieved.

B. If Substantial Completion has been achieved but Final Completion has not been achieved by the Final Completion date, Final Completion liquidated damages shall accrue each Day until Final Completion is achieved.

C. If Substantial Completion is not achieved by the time of Final Completion then liquidated damages for both Substantial and Final Completion shall run concurrently until Substantial Completion is achieved.
D. The scheduled Final Completion date shall not be extended, in any case, solely because Substantial Completion was not achieved by the scheduled Substantial Completion date.

E. This paragraph will not apply to delays in completion of the Work due to acts of God, acts of the Public Enemy, acts of the Government (in either its sovereign or contractual capacity), fires, floods, strikes, or unusually severe weather, provided, that the Contractor shall, within five (5) Days from the end of the month in which such delay occurred, notify the Owner in writing of the causes of delay and the facts relating thereto; and, provided that such delay occurs prior to the Substantial Completion date or, if Substantial Completion has been achieved, such delay occurs prior to the Final Completion date.  Failure to provide such notice shall preclude the Contractor from claiming that delays resulted from the acts of God, acts of the Public Enemy, acts of the Government (in either its sovereign or contractual capacity), fires, floods, strikes, or unusually severe weather.

F. Nothing in the above clause shall be interpreted as limiting in any way, the Owner’s right to proceed against the Contractor for additional damages or losses. Liquidated damages are for delay only and are in addition to any other rights available to the Owner by contract or law. To the fullest extent permitted by Laws and Regulations, the Contractor shall waive any defense as to the validity of such liquidated damages as set forth herein on the grounds that such liquidated damages are void as penalties or are not reasonably related to actual damages.

10.5 Weather shall be considered “unusually severe”, only if a weather condition (or any combination of weather conditions) prevents the Contractor from working a number of workdays during a calendar month, which number exceeds the number of workdays listed below for that calendar month. Delays will only be allowed for the amount of lost work days in excess of the following:

January


6

July


4

February

4

August


3

March


4

September

3

April


3

October


3

May


4

November

3

June


4

December

5

10.6 The Contractor shall anticipate the potential loss of the number of workdays listed above for each calendar month due to weather, and shall schedule the Work accordingly. Any schedules submitted shall include the above number of days each month as lost days. The Owner shall determine, upon examination of submitted evidence, whether or not weather prevented the Contractor from performing Work on the days claimed by the Contractor. The Owner’s determination shall be final and binding upon the parties.

10.7 The Work shall be considered complete when the following criteria have been met; all items of the Work have been constructed, inspected and accepted by the Owner and further that all punch list items have been corrected and the Owner has issued a letter of acceptance.

XI. SEPARATE CONTRACTS BY OWNER
11.1 The Owner reserves the right to award other contracts in connection with the Project, the work under which may proceed simultaneously with the execution of this Agreement. The Contractor shall afford other separate Contractors reasonable opportunity for the introduction and storage of their materials and the execution of their work, and the Contractor shall take all reasonable action to coordinate its Work with theirs. If the work performed by the separate Contractor is defective or so performed as to prevent the Contractor from performing the Work, the Contractor shall immediately notify the Owner upon discovering such conditions. Upon receiving notification, the Owner shall take such appropriate steps as are necessary to allow the Contractor to perform Work under the Agreement, and appropriate extensions of time and change orders will be given to the Contractor, pursuant to the Agreement, to compensate for any delays and extra costs caused by separate Contractor's performance.

XII. INDEMNIFICATION

12.1 To the fullest extent permitted by Laws and Regulations, the Contractor shall indemnify and hold harmless the Owner, the Engineer, the Engineer’s Consultants and officers, directors, employees, agents and other consultants of each and any of them from and against all claims, costs, losses and damages (including, but not limited to all fees and charges of engineers, architects, attorneys and other professionals and all court or arbitration or other dispute resolution costs) caused by, arising out of or resulting from the performance of the Work, provided that any such claim, cost, loss or damage: (i) is attributable to bodily injury, sickness, disease or death, or to injury to or destruction of tangible property (other than the Work itself), including the loss of use resulting therefrom, and (ii) is caused in whole or in part by any negligent act, errors, omissions, recklessness, or intentionally wrongful conduct of the Contractor, any Subcontractor, any supplier, any person or organization directly or indirectly employed by any of them to perform or furnish any of the Work or anyone for whose acts any of them may be liable, regardless of whether or not caused in part by a person or entity indemnified hereunder. This paragraph shall not require indemnification for a particular claim, cost, loss, or damage to the extent caused by or resulting solely from the negligence of the Owner, it agents, or employees.
12.2 In any and all claims against the Owner or any of the Owner’s consultants, agents, officers, directors, or employees by any employee (or the survivor or personal representative of such employee) of the Contractor, any Subcontractor, any supplier, any person or organization directly or indirectly employed by any of them to perform or furnish any of the Work or anyone for whose acts any of them may be liable, the indemnification obligation shall not be limited in any way by any limitation on the amount or type of damages, compensation, or benefits payable by or for the Contractor or any such Subcontractor, supplier or other person or organization under workers’ compensation acts, disability benefit acts or other employee benefit acts.

12.3 The indemnification obligations of the Contractor shall not extend to the damages caused by the Owner and the Owner’s consultants, officers, directors, employees or agents resulting from the negligent preparation or approval of, Drawings, or Specifications.

End of Section

PAGE  
[image: image1.png]


June 2016




108 - 2

Project Title

Date

Owner

Bid Number

